## Sheet1
Today: | 2018-05-17 | Date | 2017-11-30 | 2017-12-05 | 2017-12-12 | 2017-12-19 | 2017-12-26 | 2018-01-02 | 2018-01-09 | 2018-01-16 | 2018-01-23 | 2018-01-30 | 2018-02-06
Team | Bene, Geraldine, Nassim, Uwe | CW | 48 | 49 | 50 | 51 | 52 | 1 | 2 | 3 | 4 | 5 | 6
|  | SW | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17
What | Description | Who / Count | 10 | 9 | 8 | 7 | 6 | 5 | 4 | 3 | 2 | 1 | 0
Ongoing
Research | How can we do the stuff we want to do? | ALL
Documentation | javadoc in code, what we do | ALL
Organisation | Who does what, whats next, where are issues, where do we need support | ALL
Phase 01 - Research, Overview & Planning
Project Briefing | Visualizing a Self-Learning Agent to Play Pong Game | ALL
| https://drive.google.com/drive/folders/1dyFxAwSpwIutMi4__-php_-VFXAgvDta | ALL
Research | Machine Learning, Reinforcement Learning, Neural Networks | ALL
| LaTeX - basics, getting started | ALL
| javadoc | ALL
Project Planning | What needs to be done | Uwe
| When do we need to finish the tasks | Uwe
| Who does what? | ALL
Phase 02 - Concepts & Coding Easy Stuff
GUI | Concept | Nassim
| MockUp/Design | Nassim
| 4 Scenes | Nassim
| per Scene 3 Buttons | Nassim
| Testing | Nassim
Pong Game | Player vs Static AI | ALL
| Self written --> we understand the code | ALL
| Testing | ALL
Phase 03 - Learning Agents & Visualization
Pong Game | Learning Agent vs Static AI | Geraldine
| Visualizing Learning Progress of Agent | Geraldine
| Testing | Geraldine
Phase 04 - Finishing
Pong Game | as .jar file | Bene
javadoc | as .html files in zip folder | Bene & Geraldine
Documentation | write documentation | ALL
Documentation | as PDF | Uwe
Presentation | in LateX Presenter | Nasim