## Sheet1
Today: | 2018-05-17 | 2017-11-30 | 2017-12-05 | 2017-12-12 | 2017-12-19 | 2017-12-26 | 2018-01-02 | 2018-01-09 | 2018-01-16 | 2018-01-23 | 2018-01-30 | 2018-02-06
Team | Benedikt, Geraldine, Nassim, Uwe | 48 | 49 | 50 | 51 | 52 | 1 | 2 | 3 | 4 | 5 | 6
|  | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17
What | Description | 10 | 9 | 8 | 7 | 6 | 5 | 4 | 3 | 2 | 1 | 0
Ongoing
Research | How can we do the stuff we want to do?
Documentation | javadoc in code, what we do
Organisation | Who does what, whats next, where are issues, where do we need support
Phase 01 - Research, Overview & Planning
Project Briefing | Visualizing a Self-Learning Agent to Play Pong Game | bar: 48 7 to 50 9
Research | Machine Learning, Reinforcement Learning, Neural Networks | bar: 48 7 to 50 9
Project Planning | What needs to be done | bar: 50 9
Phase 02 - Concepts & Coding Easy Stuff
GUI | Concept | bar: 51 10
Pong Game | Player vs Static AI | bar: 51 10 to 1 12
Phase 03 - Learning Agents & Visualization
Pong Game | Learning Agent vs Static AI | bar: 2 13 to 4 15
Phase 04 - Finishing
Pong Game | as .jar file | bar: 5 16 to 6 17
javadoc | as .html files in zip folder | bar: 5 16 to 6 17
Documentation | write documentation | bar: 5 16 to 6 17
Documentation | as PDF | bar: 5 16 to 6 17
Presentation | in LateX Presenter | bar: 5 16 to 6 17